## Sheet1
| Sr No. | Requirements | Duration | Completion Status
| 1 | Replace word Patient by Member everywhere | 3 hours | Completed
| 2 | Mention name of relatives in contact |  | Completed
| 3 | No need of religion in personal information |  | Completed
| 4 | Add Spo2 in vitals list | 4 hours | Completed
| 5 | Add option for previous reports(multiple upload files) |  | Completed
| 6 | Add adhar number option and upload copy of adhar option (other information section) | 3 hours | Completed
| 7 | Complete the preassessment form and edit and generate pdf. | 3 days | in progress
| 8 | In blood sugar reading , need three catagories F/PP/R | 2 hours | Completed
| 9 | On discharge form: change name of Ongoing Medication to On discharge medications | 3 hours | Completed
| 10 | In On admission form---Other information..insurance details we can add TPA contact,name. |  | Completed
| 11 | Replace discharge report by discharge summary on admission,edit form |  | Completed
| 12 | show given medicine to member in dashboard |  | Completed
| 13 | Delete entries of test patients...except DKT TTK |  | Completed
2023-08-09 | 1 | Completion of pre assessment form and creating log in for users who will do assessment. You can show only pre assessment part for such users (drop down options 1. Medicine 2. Lab, 3. Physiotherapy, 4. Equipment 5. Dedicated attendant 6. Other (free text)
| 2 | Monthly bill creation in the system with the summary provided to you.
| 3 | Remove the “remove” option from medication only keep update/edit
| 4 | Add physiotherapy module as per the evaluation report shared with you, I will share protocol and daily notes format tomorrow. We may need to have similar user log in’s for physiotherapist
| 5 | Edit option in Member types (used while admitting in facility)
| 6 | Automated email framework…will share draft
| 7 | Merge Complaints and Progress Notes into one
| 8 | On dash board show up to 10 days data of progress notes, vitals, medications, intake output etc and button of view all if one wants to check all records.
| 9 | In diagnosis, we will provide list of items to be removed which are not applicable in ALF. That can be deleted.
| 10 | Back up of data as we have partially gone paperless.
| 11 | creation of lab module: log in for lab technician, facility of upload reports and view reports to all users on dashboard

## Sheet2
Sr No. | Requirements | Tentative days | Completion Status
1 | Completion of pre assessment form and creating log in for users who will do assessment. You can show only pre assessment part for such users (drop down options 1. Medicine 2. Lab, 3. Physiotherapy, 4. Equipment 5. Dedicated attendant 6. Other (free text)
2 | Monthly bill creation in the system with the summary provided to you.
3 | Remove the “remove” option from medication only keep update/edit
4 | Add physiotherapy module as per the evaluation report shared with you, I will share protocol and daily notes format tomorrow. We may need to have similar user log in’s for physiotherapist
5 | Edit option in Member types (used while admitting in facility)
6 | Automated email framework…will share draft
7 | Merge Complaints and Progress Notes into one
8 | On dash board show up to 10 days data of progress notes, vitals, medications, intake output etc and button of view all if one wants to check all records.
9 | In diagnosis, we will provide list of items to be removed which are not applicable in ALF. That can be deleted.
10 | Back up of data as we have partially gone paperless.
11 | creation of lab module: log in for lab technician, facility of upload reports and view reports to all users on dashboard