## Ashwini
Activity Tracker
Date:01 Oct-15 Oct
Team Leader: | Ashwini Patil
Team Member:
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | MEMS | Coding & Development
|  |  | NHM Report - BV - Ambulance Staff performance Report & Counts mismatch - BVII - Ambulance vehical offroad data - AI - SAM Report - AII - 108 NHM Report -Annexure B-VII Vehicle Status Info Report -Annexure B-V Ambulance staff performance Report's -Annexure A-I -Annexure B-I Distance Running Statement -Summary Report -Annexure B-VI Ambulance staff performance Report | 16 hr | 20 hr | Count missmatch issues
|  |  | ERC Reports - Breakdown Report - Bike Report Issue - DCO Closure Report [ Validation ] | 2 hr | 4 hr | In DCO Module Condition handle
|  |  | ERCP Lising issue - Assign calls duplication | 2 hr | 1 hr | only condition handled for login users
|  |  | DCO Issues - Single reports - Receiving Hospital - Provider impressions - Validation - Pages changes | 4hr | 5hr
|  |  | Inspection-Grievance Flow Flow - Inspection ID issue resolved - Forword to Grievance Desk - Display in Grievance Dashboard | 8 hr | 6 hr
|  |  | NHM Dashboard Cron | 2 hr | 1 hr | Need to Cron Login Changes [ Ashok Sir, Chaitali mam Disscussion ]
2 | JK Ems | Coding & Development | NHM - District wise & ambulance wise cron changes | 8 hr | 8 hr
|  |  | Report - Dispatch Closure Summery Report [ Count mismatch issue ] - Incident Report - DCO Closure Report - Issue - Feedback Report issue - Employee Call Status Issue - Call Count AHT report - Daily Report issue | 16 hr | 16 hr
|  |  | Caller Relation - ERO 102 | 1 hr | 2 hr
|  |  | Duplicate incident ID Add district filter- ERO 108 & 102 | 1 hr | 1 hr
|  |  | Quality forms issue | 1 hr | 1 hr
|  |  | Fuel filling & Oxygen filling issue | 2 hr | 2 hr
|  |  | Ambulance Module Report | 0.5 hr | 0.5 hr
|  |  | Fuel Station Issue | 1 hr | 1 hr
|  |  | RTM listing issue | 0.5 hr | 0.5 hr
3 | Spero | Tech Support | RMS Voice File Backup | 1 hr | 1 hr
|  |  | Bulk SMS send | 1 hr | 1 hr
4 | Meeting |  | Meeting with Praveen Sir,Krushna,Varsha for KRA | 1 hr | 3 hr
|  |  | Meeting with - Team Leaders | 3 hr | 5 hr
|  |  | ALF Meeting - Shiv Sir,Balaji,Akshata,Yogita | 2 hr | 4 hr | Explain all flow
- Meeting with Team

## Balaji Muttepowar
Activity Tracker
Date:01 Oct-15 Oct
Team Leader: | Ashwini Patil
Team Member: | Balaji Muttepowar
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | ALF | Coding & Development | Added floor,allocated room, column on dashboard. | 4 hours | 4 hours
2 |  |  | Added pagination on dashboard. | 8 hours | 10 hours | on this page,add 6 pagination facing issue to handle pagination data
3 |  |  | Merged complain and progress note in all module | 5 hours | 5 hours
4 |  |  | Changes in nurse module. | 3 hours | 3 hours
|  |  | Created Preassessment pdf. - working on preassessment pdf design. - personal detail section. - family section. - children section. - immunization history. - general examination. - psychological & Behavioural condition. - barthel index. -fall risk assessment. | 16 hours | 10 hours | no need to extra effort because chat gpt have given solution soon as per expected.
|  |  | Doctor module - Added delete medicine option by doctor. | 3 hours | 3 hours
Addmission form - Changes
|  |  | Fetch patient data according to select preassessment no. | 5 hours | 6 hours | facing issue on preassessment dropdown first time is working proper but next time not manage data
|  |  | Added preassessment medicine list when select preassessment no. | 5 hours | 5 hours
|  |  | facing issue on preassessment pdf design form and solved it. | 5 hours | 5 hours
|  |  | Added preassessment dropdown in addpatients view by coordinator. | 3 hours | 3 hours
|  |  | Add muiltiple treating doctor | 5 hours | 6 hours | facing issue on handling data
|  | Testing | Test preassessment module. | 6 hours | 6 hours
|  | Database Work | Database work - pre-assessment changes | 4 hours | 4 hours
|  | Meeting | A] PreAssesment Changes & requirements and fetch data on admision form when select preassessment no. | 2 hours | 4 hours

## Ashfiya
Activity Tracker
Date:01 Oct-15 Oct
Team Leader: | Ashwini Patil
Team Member: | Ashfiya Momin
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | MEMS | Coding & Development
|  |  | Samrudhi ERC Report - Closure Report - incident datewise | 4 hr | 2 hr
|  |  | Samrudhi NHM Report - Samruddhi Annexure A-I report - Samruddhi Annexure A-II report - Samruddhi Annexure B-V 108 EMSO Details shown. Need to show only Samruddhi EMSO -MDT login report - B-VII Ambulance performance report | 16 hr | 24 hr | 1. Not able to code understand proerly 2. but she tried
|  |  | Annexure B-I - Hospital Name Shows in the report instead of Base Locations Name Annexure B-II-B - Remove Report Annexure B-III - Shows Blank Data | 16 hr | 16 hr

## Nabha
Activity Tracker
Date:01 Oct-15 Oct
Team Leader: | Ashwini Patil
Team Member: | Nabha Chitnis
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | HHC aggigation | discussion | about the requirement and database structure | 9hrs | 20 hrs | work getting stuck as some issues with server
2 |  | test plan | created test plan doing master plan | 7 hrs | 2 hr | In-Progrsss
3 |  | test scanario | https://docs.google.com/spreadsheets/d/14G-lszt2NPj4KWXLZoNVsKnN4j0sxTqe/edit?usp=drive_link&ouid=106691316691796219257&rtpof=true&sd=true | 6 hrs | 9 hrs
4 |  | test cases | https://drive.google.com/drive/folders/1Pi6bzhn7SwDOaLfPwECzXdX8JtXkHvmB | 8 hrs | 8 hrs
5 |  | Bug List | https://docs.google.com/spreadsheets/d/1qjJDvSS_H7lkyJq5HaZetJGqH9ltHByn/edit?usp=drive_link&ouid=106691316691796219257&rtpof=true&sd=true | 25 hrs | 25 hrs
6 | ALF | testing | overview of requirment, basic testing Admin and doctor module | 8 hrs | 9 hrs

## Akshta
Activity Tracker
Date:01 Oct-15 Oct
Team Leader: | Ashwini Patil
Team Member: | Akshta More
Sr.no | Project Name | Activity | Description | Estimated hours | Actual hours | Remarks/Blockers
1 | ALF | Coding & Design
|  |  | Work on Preassessment Form on AlF Project | 3:20 h | 3:20 h
|  |  | Worked on Preassessment PDf UI | 4:07 h | 4:07 h
|  |  | Understanding Coding of AlF Project | 4:55 h | 4:55 h
|  |  | Attending Meeting & Testing Flow of Project | 5:00 h | 5:00 h
|  |  | Changes in UI | 4:30 h | 4:30 h
|  |  | Worked On Admission Form | 4:45 h | 4:45 h
|  |  | Checking Responsiveness & doing changes on that | 3:45 h | 3:45 h